## Sheet1
| Richmond Transportation Committee Project Pipeline | [5 empty] | Updated: 4/16/24 (based on 11/28/23)
Project Name | Project Description | Capital Budget Item | Project Initiation | Phase * | Phase Completed | Report | Next Steps | Estimated Construction Cost | Grant Funding
Bridge Street - East Side New Sidewalk | New sidewalk on east side of Bridge Street between Jolina court and Esplanade Street/ Volunteers Green | No | 2021 | Final Design | SC | https://studiesandreports.ccrpcvt.org/wp-content/uploads/2022/11/Richmond_Scoping_Report_FINAL_9_23_2022.pdf | Sidewalk draft design plans prepared with CCRPC serving as project manager | $275,000 including $64,000 town match | Received Vtrans TAP Grant and town ARPA funds for local match
Bridge Street Redesign - Complete Streets | New sidewalk between Rt. 2 and Jolina Court along with multi-modal improvements to Bridge Street corridor | No | 2020 | Final Design | SC | https://studiesandreports.ccrpcvt.org/wp-content/uploads/2021/09/20210827_RichmondBridgeStreet_ScopingMemo_WithAppendices.pdf | Sidewalk draft design plans prepared | $219,509 plus $35,000 project mgt | Town ARPA Fund
Intersection of THBC roads | Intersection includes Thompson Road, Huntington Road, Bridge Street, and Cochran Road - difficult intersection for pedestrians, bicycles, and vehicles | No | 2020 | SC |  | https://studiesandreports.ccrpcvt.org/wp-content/uploads/2021/09/20210827_RichmondBridgeStreet_ScopingMemo_WithAppendices.pdf | April 2024 - RTC made recommendations to Selectboard on VHB alternative or four way stop; Selectboard holding public discussion on May 6 | $72,697 for VHB alternative and $100,000 for four-way stop | Future TBD
Jericho Road Western Sidewalk Project | Construct new sidewalk on Jericho Road from the school entrance to 1) Southview; 2) Valley View Road | FY27 | 2021 | SC | SC | https://studiesandreports.ccrpcvt.org/wp-content/uploads/2022/11/Richmond_Scoping_Report_FINAL_9_23_2022.pdf | In fall 2023, notified we did not get funding for 2023 Bicycle & Pedestrian Program for School Street to Southview. Will communicate with interested neighbors and general public. | $520,000 Const./ $720,000 Total | Future TBD - See state response. Set link here.
Huntington Road to Johnnie Brook trail | Huntington Road from Farr Complex to the Cross Vermont Trails trailhad at Johnnie Brook trail | FY27 | 2021 | SC | SC | https://studiesandreports.ccrpcvt.org/wp-content/uploads/2022/11/Richmond_Scoping_Report_FINAL_9_23_2022.pdf | Additional scoping study needed for "S" curve area; Funding to be sought. Farr's concerned with safety aspects of the project area. Get costs for moving house and then seek a grant (including costs to move house). | TBD | Future TBD
East Main Street | Re-construct sidewalks on south and north side of East Main Street btween Bridge Street & Harrington's | No | 2021 | IC | Scheduled for construction by Richmond Highway. | https://www.richmondvt.gov/fileadmin/files/Archive/2018/11/3f-Richmond-Highway-restructuring-and-staffing-proposal.pdf | Town Highway Dept. to do sidewalk replacement in summer 2024, starting with new curbing | 283543 | No grant funding, covered in town budget
Bike/Ped Master Plans | Master Complete Streets plan to guide the for ped and bike on and off-road connections and trails | No
A. Northern Area | Master Plan covers area north of Winooski River |  | 2020 | Complete | PL | https://www.richmondvt.gov/fileadmin/files/Departments/Planning_Zoning/Richmond_Bike_Walk_Trails_Plan_2021-06-17.pdf | Integrate report findings into projects as appropriate |  | Future TBD
B. Southern Area | Master Plan covers area south of Winooski River |  | 2021 | Complete | PL | https://www.ccrpcvt.org/wp-content/uploads/2022/09/20220914_RichmondBikeWalkTrailsFINAL.pdf | Cochran Road feasibility and scoping project beginning fall 2023 |  | FY24 UPWP
Route 2 Targeted Scoping for Improving Shoulder Widths | Increase shoulder width at specific points between Village and Park and Ride, following the VTrans repaving project of Route 2 | No | 2022 | SC | Scoping | https://www.richmondvt.gov/fileadmin/files/Transportation_Committee/Meetings/2023/08/TechnicalFeasibilityMemo_20230817_FINAL_Rt._2_Pinchpoint.pdf | Presentation to Selectboard with final recommendations Nov. 6, 2023. Requires additional info and discussions with VTrans and CCRCP. Debrief from SB Meeting |  | FY23 UPWP
Cochran Road Corridor Study | Three elements: Corridor Study for on and off road improvements; Scoping Study for Richmond village and Jonesville segments; Permanent traffic calming priorities throughout entire length | No | 2023 | SC & Feas. Study | Contractor selected - WSP |  | Project began in March 2024; local concerns meeting held April 9, 2024 | TBD | FY24 UPWP
Richmond Gateway Scoping Study | Bicycle and pedestrian connections between Richmond Village, elementary/middle school campus, mobile home park and the exit 11 Park and Ride. Uses 2014 study and 2021 Bike/Ped Master Plan North End reports | No | 2022 | SC | Scoping in-progress |  | Consultants to present report to Selectboard on May 20, 2024 | TBD | FY23 UPWP
Town Plan Goals & Objectives Review | Town Plan: review goals and objectives related to transportation planning | No | 2021 | PL | 2021-08-10 | Document submitted to Planning Commission | Overdue?; Annual Review and/or Planning Commission request. Start reviewing progress quarterly.
Richmond Capital Budget/Plan | RTC review and recommend items |  | 2021 | PL | 3/1/2021 Reviewed FY23 Plan | SEE TOWN WEB SITE FOR CURRENT PLAN | RTC review FY26 Plan in fall 2024
Green Mountain Transit Richmond Services | Green Mountain Transit Plan with Richmond element |  | 2022 | PL | Completed Part of FY23 UPWP GMT Grant | https://www.richmondvt.gov/fileadmin/files/Selectboard/Meetings/2023/06/3c_Memo_Regarding_Transit_Service_In_Richmond.pdf | Consultants presentation to Selectboard June 5, 2023. No plans at this time |  | FY23 UPWP - no further funding at this time
Walkability Audit Project and Report | Audit to assess quality needed improvements for ped and bicycle infrastructure |  | 2022 | SC | Report presented to Selectboard June 2023 | https://www.richmondvt.gov/fileadmin/files/Selectboard/Meetings/2023/06/3c_Richmond_Sidewalk_Audit_-_4-28-2023_new.pdf | Report available. Elements of report to be integrated into specific projects. VHB provided report for Bridge St sidewalk project design |  | Future TBD
Committee Documents
A. Public Participation Plan | Created short and long versions |  |  | PL | Adopted 6/4/2020 | https://www.richmondvt.gov/fileadmin/files/Transportation_Committee/General/Transportation_Committee-Public_Participation_Plan_2020-06-04_FINAL.pdf | Update as needed | NA
B. Transportation Implementation Plan | Created and provided to Selectboard |  |  | PL | Adopted 6/4/2020 | https://www.richmondvt.gov/fileadmin/files/Transportation_Committee/General/RTC-Trans-Implementation-Plan-2020-06-04-FINAL.pdf | Update as needed | NA
C. Committee Goals | Created and provided to Selectboard |  |  | PL | Adopted 6/4/2020 | [will add link to this file on town web site] | Update as needed | NA
COMMITTEE NO LONGER PURSUING
Bike/Ped Master Plans into Official Map | Official Map to regulate development of infrastructure and possibly include ped and bike enhancements |  | ON HOLD | PL |  |  | Was scheduled to begin January 2023 with CCRPC staff; Planning Commission wished to defer the project - may or may not be taken up in future |  | FY23 UPWP (Awarded but not commenced)
* Phases: PL = Planning; Project Design/Definition=PD; Scoping=SC: Engineering=EN; Permitting=PT; In Construction=IC;
Maintenance& Operation=MO