## Sheet1
Activity | Category | Planned Start Year | Planned Start Date | Due Date | Committe Owner | Lead Owner | Supporting Members | Description | Comments
Revise the zoning and subdivision regulations to allow housing in the Commercial and Village Commercial districts close to the village center | Zoning Recommendations | 2026 |  |  | Planning Commission | Virginia
Expand the current density bonus program to all zoning districts | Zoning Recommendations | 2026 |  |  | Planning Commission | Virginia |  |  | Late 2026, may push to 2027
Investigate increasing the maximum allowable height of buildings in Richmond by one story beyond those instances that are mandated by state statute (i.e., qualifying affordable housing developments) | Zoning Recommendations | TBD |  |  | Planning Commission |  |  |  | Not on roadmap currently. Community discussion would be needed.
Work with the Planning and Zoning Office to revise zoning and subdivision application forms, procedures, and regulations, as needed, to emphasize transparency and clarity, and to manage applicant expectations. | Zoning Recommendations | 2026 |  |  | Planning Commission | Virginia | Keith (Town Planner) |  | RHC can provide support
Develop a template letter and guildeines for the Town Manager to send letters of support when requested for projects. | Successfully Funding Affordable Housing Projects | 2026 |  |  | RHC |  |  | RHC to draft a template letter RHC to develop guidelines for when to send | There is a folder in the RHC OneDrive with sample letters. These were provided by Miranda Lescaze, who could help review a draft of guideliens or template.
Create a Housing Trust Fund | Successfully Funding Affordable Housing Projects | 2026 |  | 2027 | RHC |  |  | Create a plan for how to set up a fund, and then establish the fund in 2027 | Steps: Define steps on how to set this up. Present plan Define rules for spending/funding Seek legal support
Develop a Master Plan for the gateway, which will provide a future-focused, 20–30-year plan for how the town envisions future development in the Gateway. | Successfully Funding Affordable Housing Projects | 2028 |  |  | RHC |  |  |  | Steps: First- Seek a funding source to help pay for this effort.
Partner with housing organizations such as Habitat for Humanity, Champlain Housing Trust Fund, and/or Cathedral Square to support the development of future community projects. | Successfully Funding Affordable Housing Projects | 2026 |  |  | RHC |  |  |  | Look into Borden St. Housing project. This was developed by CHT. Is there a campaign to run for finding land for Habitat to use?
Utilize the recently passed Community and Housing Infrastructure Program2 (CHIP) to unlock financial support for improvements such as water, sewer, roads, and stormwater systems to support the growth of all housing types. | Successfully Funding Affordable Housing Projects | 2025 |  |  | RHC |  |  |  | Meeting on Oct. 29, a CHIP meeting could help inform this effort
Work with the Water and Sewer Commission to review and update the existing water and sewer bylaws to increase the likelihood of district expansion. | Water and Sewer Regulation/Policy revisions | 2025 |  |  | RHC |  |  |  | Dec. 1 the committee was invited to an upcoming Water/Sewer committe meeting.