## FY24 Highway Equipment
HIGHWAY EQUIPMENT | License Plate # | Year of Equipment | FY Acquired | Estimated Life | Description | Acquired Amount | Payment Source Status | Curent Payment Source | Beginning Reserve Balance | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39
Dump Truck #1 | AAR879 | 2022 | FY22 | 7 | International 7600 Tandem | 124222 | Complete Note FY20 |  |  | FY29: 225000; FY36: 275000
99222
Dump Truck #2 | AAX405 | 2020 | FY20 | 7 | International HV507 Single | 172530 | Note FY25 | Union Bank -Principal |  | FY23: 26920; FY24: 26920; FY25: 26920; FY27: 225000; FY34: 250000
[7 empty] | 134602 | Unon Bank - Interest |  | FY23: 1543; FY24: 1030; FY25: 513
Dump Truck #3 | AAR879 | 2015 | FY16 | 7 | International 7600 Tandem | 132612 | Complete Note FY21 |  |  | FY23: 206884; FY30: 250000; FY37: 275000
113214
Dump Truck #4 | AAW242 | 2019 | FY19 | 7 | International HV613 | 133405 | Note FY24 | Union Bank - Principal |  | FY23: 26500; FY24: 24000; FY26: 225000; FY33: 250000
[7 empty] | 103500 | Union Bank - Interest |  | FY23: 929; FY24: 442
Truck & Snow Plow - 1 ton #5 | AAW336 | 2019 | FY19 | 7 | Ford F550 | 68696 | Complete Cash GF |  |  | FY26: 90000; FY33: 100000
Truck & Snow Plow - 1 ton #6 | AAP834 | 2021 | FY21 | 7 | Chevy 3500 | 46280 | Complete Cash GF |  |  | FY29: 90000; FY36: 110000
Pickup and Snowplow #7 Foreman | AAT218 | 2017 | FY17 | 7 | Chevy 2500 | 56280 | Complete Note GF |  |  | FY24: 78000; FY31: 100000; FY38: 110000
Road Grader #8 | AAW528 | 2017 | FY19 | 12 | John Deere 772GP | 308344 | Note FY24 | Union Bank - Principal |  | FY23: 30000; FY24: 30000; FY29: 500000
[7 empty] | 120000 | Union Bank - Interest |  | FY23: 1104; FY24: 553
Bucket Loader #9 | AAR334 | 2012 | FY14 | 10 | John Deere 524K used | 112821 | Complete Note GF |  |  | FY23: 175000; FY33: 175000
Excavator used #10 | ?? | 2021 | FY22 | 15 | Hitachi 190W | 275000 | Complete Cash GF |  |  | FY23: 275000; FY38: 275000
Tractor/Mower Challenger #11 | AAP855 | 2008 | FY11 | 11 | Challenger MT445B | 66500 | Complete Cash GF |  |  | FY24: 125000; FY35: 110000
Tractor Kubota #12 |  | 2018 | FY19 | 8 | Kubota 1880 | 12750 | Complete Cash GF |  |  | FY26: 12750; FY34: 12750
Tractor Ventrac #13 | AAT593 | 2016 | FY17 | 8 | Ventrac with attachments | 45667 | Complete Cash GF |  |  | FY25: 52000; FY33: 52000
Pressure washer trailer | AAM348 | 2008 | FY19 | 10 | North Star | 8063 | Complete Cash GF |  |  | FY28: 10000; FY38: 10000
Trench Box |  | 2019 | FY20 | 30 | Trench Box | 9195 | Complete Cash GF
Generator |  | 2020 | FY21 | 20 | Genrator | 13692 | Complete Cash GF
Traffic signs |  | 2015 | FY16 | 15 | Portable traffic signs | 10950 | Complete Cash GF |  |  | FY30: 12000
Trade-In Dump Truck | [9 empty] | FY23: -31884; FY26: -60000; FY27: -60000; FY29: -60000; FY30: -60000; FY33: -60000; FY34: -60000; FY36: -60000; FY37: -60000; FY38: -60000
Trade-In Pickup Truck | [9 empty] | FY24: -25000; FY26: -15000; FY29: -15000; FY31: -15000; FY33: -15000; FY36: -15000
Trade-In Road Grader | [9 empty] | FY29: -150000
Trade-in Bucket Loader | [9 empty] | FY23: -45000; FY33: -45000
Trade-in Excavator | [9 empty] | FY23: -50000; FY38: -50000
Trade-in Miscellaneous | [9 empty] | FY24: -25000
Unnasinged Funds | [9 empty] | FY23: -50750
Restricted Funds | [9 empty] | FY23: -415000
Capital Reserves used | [9 empty] | 0 | -153000 | -52000 | -252750 | -165000 | -10000 | -590000 | -202000 | -85000 |  | -457000 | -202750 | -110000 | -310000 | -215000 | -285000 | 0
.
Remaining balance | [9 empty] | 151246 | 82945 | 27433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan Payments from Taxes | [9 empty] | FY23: -86996; FY24: -82945; FY25: -27433
Payment from Taxes | [9 empty] | FY23: -17500
Payment from Taxes | [9 empty] | FY23: -13000
Payment from Taxes | [9 empty] | FY23: -33750
Reconciliation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reserves raised from Taxes | [9 empty] | -25000 | -50000 | -200000 | -200000 | -225000 | -225000 | -225000 | -200000 | -200000 | -200000 | -200000 | -200000 | -225000 | -225000 | -225000 | -225000 | -225000
Total Taxes raised | [9 empty] | -176246 | -132945 | -227433 | -200000 | -225000 | -225000 | -225000 | -200000 | -200000 | -200000 | -200000 | -200000 | -225000 | -225000 | -225000 | -225000 | -225000
Capital Reserve at FY end | [8 empty] | 93701.04 | 118701.04 | 15701.04 | 163701.04 | 110951.04 | 170951.04 | 385951.04 | 20951.04 | 18951.04 | 133951.04 | 333951.04 | 76951.04 | 74201.04 | 189201.04 | 104201.04 | 114201.04 | 54201.04 | 279201.04
Note on L42: Finance: Tractor

## FY24 Highway Infrastructure
HIGHWAY INFRASTRUCTURE | FY Acquired | Acquired Amount | Beginning Reserve Balance | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39
Millet Street Loan |  | 116000 |  | FY23: 5780; FY24: 5962.66; FY25: 6013.93; FY26: 6134.26; FY27: 6256.89; FY28: 6380; FY29: 6542.94; FY30: 6639.85; FY31: 6772.65; FY32: 6908.1
|  |  |  | 1265 | 1150.25 | 1002.34 | 912.73 | 789.38 | 664.25 | 356.61 | 403.41 | 273.62 | 138.16
Jericho Road Loan |  | 688800 |  | FY23: 43200; FY24: 43200; FY25: 43200; FY26: 43200; FY27: 43200; FY28: 43200; FY29: 43200; FY30: 43200; FY31: 43200; FY32: 43200
|  |  |  | 17387 | 15761 | 14068 | 12312 | 10503 | 8652 | 6743 | 4847 | 2891 | 26
Paving/Retreatment (12 year cycle) |  |  |  | 294000 | 294000 | 294000 | 295000 | 295000 | 298000 | 298000 | 300000 | 300000 | 305000 | 305000 | 310000 | 310000 | 315000 | 315000 | 315000 | 315000
Gravel Plan (7 year cycle) |  |  |  | 140000 | 140000 | 145000 | 145000 | 145000 | 145000 | 145000 | 145000 | 145000 | 150000 | 150000 | 150000 | 155000 | 155000 | 155000 | 155000 | 155000
Sidewalk & Stormwater routine maintenance |  |  |  | 120000 | 125000 | 130000 | 135000 | 140000 | 25000 | 25000 | 25000 | 25000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
Southview Drive Bridge |  |  |  | FY31: 1000000
Southview Guardrail Project |  |  |  | FY25: 40000
Bates Farm Culvert Crossing Guardrail Project |  |  |  | FY28: 30000
Unnasinged Funds
Unnasigned Restricted Funds
Bridge & Culvert Reserves Used |  |  |  | FY31: -1000000
Guardrail Reserves Used |  |  |  | FY25: -40000; FY28: -30000
Remaining balance |  |  |  | 621632 | 625073.91 | 633284.27 | 637558.99 | 640749.27 | 526896.25 | 524842.55 | 525090.26 | 523137.27 | 555272.26 | 505000 | 510000 | 515000 | 520000 | 520000 | 520000 | 520000
Loan Payments from Taxes |  |  |  | -67632 | -66073.91 | -64284.27 | -62558.99 | -60749.27 | -58896.25 | -56842.55 | -55090.26 | -53137.27 | -50272.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Payment from Taxes |  |  |  | -554000 | -559000 | -569000 | -575000 | -580000 | -468000 | -468000 | -470000 | -470000 | -505000 | -505000 | -510000 | -515000 | -520000 | -520000 | -520000 | -520000
Reconciliation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bridge & Culvert Reserves raised from taxes |  |  |  | -37000 | -37000 | -75000 | -75000 | -75000 | -75000 | -75000 | -125000 | -125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Guardrail Reserves raised from taxes |  |  |  | -5000 | -15000 | -11000 | -10000 | -10000 | -10000 | -10000 | -10000 | -10000 | -10000 | -10000 | -10000 | -20000 | -20000 | -20000 | -20000 | -20000
Total Taxes raised |  |  |  | -663632 | -677073.91 | -719284.27 | -722558.99 | -725749.27 | -611896.25 | -609842.55 | -660090.26 | -658137.27 | -565272.26 | -515000 | -520000 | -535000 | -540000 | -540000 | -540000 | -540000
Bridge & Culvert Reserves at FY end |  |  | 344926 | 381926 | 418926 | 493926 | 568926 | 643926 | 718926 | 793926 | 918926 | 43926 | 43926 | 43926 | 43926 | 43926 | 43926 | 43926 | 43926 | 43926
Guardrail Reserves at FY end |  |  | 9016 | 14016 | 29016 | 16 | 10016 | 20016 | 16 | 10016 | 20016 | 30016 | 40016 | 50016 | 60016 | 80016 | 100016 | 120016 | 140016 | 160016
Total Reserves |  |  | 353942 | 395942 | 447942 | 493942 | 578942 | 663942 | 718942 | 803942 | 938942 | 73942 | 83942 | 93942 | 103942 | 123942 | 143942 | 163942 | 183942 | 203942
When are we using guardrail reserves
Need to update the Paving, Gravel Plan, and Sidewalk maintenance numbers

## FY24 New Sidewalk Projects
HIGHWAY INFRASTRUCTURE | FY Acquired | Acquired Amount | Beginning Reserve Balance | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39
Bridge Street Phase 1 Jolina to Esplanad | FY24-FY25 | 325000 |  | FY24: 81250; FY25: 81250; FY26: 81250; FY27: 81250
Bridge Street Phase 2 Jolina to Big Spruce | FY26-FY27 | 332200 |  | FY26: 83000; FY27: 83000; FY28: 83000; FY29: 83000
Jericho Road Sidewalk | FY27 | 1000000 |  | FY36: 1000000
Huntington Road Sidewalk | bar: FY27
Unnasinged Funds
Unnasigned Restricted Funds
Grant for Bridge St - Phase 1 80% |  |  |  | FY24: -65000; FY25: -65000; FY26: -65000; FY27: -65000
Grant for Bridge St - Phase 2 80% |  |  |  | FY26: -66400; FY27: -66400; FY28: -66400; FY29: -66400
Grant for Jericho Road | bar: FY27
Sidewalk Reserves Used |  |  |  | FY24: -16250; FY25: -16250; FY26: -32850; FY27: -32850; FY28: -16600; FY29: -16600; FY36: -663600
Remaining balance |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336400 | 0 | 0 | 0
Loan Payments from Taxes |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Payment from Taxes |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -336400 | 0 | 0 | 0
Sidewalk Reserves raised from taxes |  |  |  | -30000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -75000 | -75000 | -75000 | -75000 | -75000 | -100000 | 0 | 0 | 0 | 0
Total Taxes raised |  |  |  | -30000 | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -75000 | -75000 | -75000 | -75000 | -75000 | -100000 | -336400 | 0 | 0 | 0
Sidewalk Reserves at FY end |  |  | 10000 | 40000 | 48750 | 57500 | 49650 | 41800 | 50200 | 58600 | 133600 | 208600 | 283600 | 358600 | 433600 | 533600 | -130000 | -130000 | -130000 | -130000
Note on I8: Finance: Push project out to FY36
Note on R8: Finance: Moved from FY27 Budget for entire amount
Note on I10: Finance: Was scheduled in FY26 at a cost of 1 million. Project has been cancelled.
Note on I16: Finance: No grants awarded for Jericho Road

## FY24 Police
POLICE EQUIPMENT | Year of Equipment | FY Acquired | Estimated Life | Description | Acquired Amount | Payment Source Status | Beginning Reserve Balance | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39
Police Cruiser #1 | 2017 | FY18 | 4 | Ford Interceptor | 38764 | Complete lease (3yr) GF |  | FY25: 50000; FY29: 62000; FY33: 77000; FY37: 9500
Police Cruiser #2 | 2021 | FY22 | 4 | Tesla | 57344 | Cash |  | FY23: 45000; FY27: 56000; FY31: 69000; FY35: 85000; FY39: 105000
Police Cruiser #3 | 2017 | FY17 | 4 | Ford Interceptor | 35258 | Complete lease (3yr) GF |  | FY25: 50000; FY29: 62000; FY33: 77000; FY37: 95000
Police Cruiser #4 | 2022 | FY23 | 4 | Dodge Durango | 45078.6 | Cash |  | FY28: 59000; FY32: 73000; FY36: 90000 | 111000
Police Cruiser #5 | 2019 | FY19 | 4 | Ford Interceptor | 41148 | Cash |  | FY26: 53000; FY30: 65000; FY34: 80900; FY38: 100000
Police Cruiser #6 | 2020 | FY20 | 4 | Dodge Durango | 40213 | Cash |  | FY27: 56000; FY31: 69000; FY35: 85000; FY39: 105000
Dash cameras |  |  | 4 | Need 6, purchase with new cruisers |  | Cash |  | 5000 |  | 10000 | 5250 | 11000 | 5800 | 12200 | 6400 | 13400 | 7000 | 14800 | 7800 | 16300 | 8600 | 18000 | 10000 | 20000 | 10500
Cruiser Emergency Equip. |  |  |  | One set for each vehicle (blue lights, siren, control box, cage, lap top stand) |  | Cash |  | 8000 |  | 18000 | 9300 | 19500 | 10200 | 21500 | 11300 | 23700 | 12400 | 26000 | 13700 | 28700 | 15100 | 31700 | 16600 | 35000 | 18300
Mobile Data Computers |  |  | 4 | Need 6, purchase with new cruisers |  | Cash |  | 6500 |  | 14300 | 7500 | 15800 | 8300 | 17400 | 9100 | 19200 | 10100 | 21200 | 11100 | 23300 | 12300 | 25700 | 13500 | 28400 | 14900
Body Cameras |  |  | 4 | Need 6 |  | Cash |  | FY28: 12500; FY32: 15000; FY36: 17500 | 20000
Trade In Police Cruiser | [7 empty] | FY23: -37000
Unnasinged Funds
Capital Reserves used | [7 empty] | -27500 | 0 | -142300 | -75050 | -158300 | -83300 | -175100 | -91800 | -194300 | -102500 | -216000 | -113500 | -238300 | -126000 | -179900 | -140100 | -293400 | -154700
Remaining balance | [7 empty] | 0 | 0 |  | 0 | 0 | 12500 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 17500 | 0 | 0 | 0 | 20000
Loan Payments from Taxes
Payment from Taxes | [7 empty] | 0 | 0 |  | 0 | 0 | -12500 | 0 | 0 | 0 | -15000 | 0 | 0 | 0 | -17500 | 0 | 0 | 0 | -20000
Reconciliation | [7 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital Reserves raised from taxes | [7 empty] | -74250 | 0 | -100000 | -100000 | -100000 | -100000 | -150000 | -150000 | -150000 | -150000 | -170000 | -170000 | -170000 | -170000 | -170000 | -170000 | -225000 | -225000
Total Taxes raised | [7 empty] | -74250 | 0 | -100000 | -100000 | -100000 | -112500 | -150000 | -150000 | -150000 | -165000 | -170000 | -170000 | -170000 | -187500 | -170000 | -170000 | -225000 | -245000
Reserves at FY end | [6 empty] | 40783 | 87533 | 87533 | 45233 | 70183 | 11883 | 28583 | 3483 | 61683 | 17383 | 64883 | 18883 | 75383 | 7083 | 51083 | 41183 | 71083 | 2683 | 72983
Note on C5: Finance: Should have been FY21 but were unable to purchase and take possession until August of FY22
Note on I5: Finance: Tesla replacement - cost based on the 2022 cruiser purchased
Note on C9: Finance: Purchased in FY22 but did not take possession until FY23
Note on I30: Finance: Was 59,500
Note on I32: Finance: was zero

## FY24 Fire
FIRE DEPARTMENT EQUIPMENT | Year of Equipment | FY Acquired | Estimated Life | Description | Acquired Amount | Payment Source Status | Curent Payment Source | Beginning Reserve Balance | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39
Fire Engine #1 (change to small pumper) | 2011 | FY11 | 20 | HME Pumper/Tanker | 363883 | Complete |  |  | FY31: 500000
Fire Engine #2 | 2015 | FY16 | 20 | Spartan Pumper/Tanker | 386164 | Complete Note |  |  | FY35: 900000
358005
Fire Engine #3 | 2018 | FY19 | 20 | International 7500 pumper/tanker | 384542 | Note FY26 | Union Bank - principal |  | FY23: 48572; FY24: 48572; FY25: 48572; FY26: 48572; FY38: 900000
[6 empty] | 291429 | Union Bank - interest |  | FY23: 4138; FY24: 3109; FY25: 2065; FY26: 1035
Rescue Truck #4 | 2005 | FY06 | 15 | International 4400 Utility Truck | 199534 | Bond FY26 | VMBB - principal |  | FY23: 10000; FY24: 10000; FY25: 10000; FY26: 10000; FY27: 700000
[6 empty] | 154471 | VMBB - interest |  | FY23: 965; FY24: 517; FY25: 126; FY26: -65
Brush Truck | 2009 | FY09 | 10 | Chevrolet Brush/Safety | 52236 | Complete |  |  | FY23: 0; FY24: 0; FY25: 267230; FY35: 300000
Repeater | 2020 | FY21 | 10 |  | 19480 | Complete Cash GF |  |  | FY31: 20000
Jaws of Life #1 | 2004 | FY05 | 15 | Portable unit stored on Enging #1 |  | Complete Cash GF |  |  | FY24: 25000
Jaws of Life #2 | 2009 | FY09 | 15 | Stationary unit stored on Rescue truck |  | Complete Cash GF |  |  | FY27: 45000
Jaws of Life #3 | 2021 | FY21 | 15 | Portable unit stored on Engine #2 |  |  |  |  | FY36: 25000
Thermal Imaging Camera |  |  | 7 |  | 9150 | Cash GF |  |  | FY23: 9150
Stabilizer Kit |  |  |  |  | 8400 | Cash GF |  |  | FY23: 8400
Air Compressor #1 | 2005 | FY05 | 15 | used to fill the air bottles. |  | Complete Cash GF |  |  | FY23: 45729
Safety Equipment
Air Packs |  |  | 15 | Need 17 (Rescue (5), Engine #1 (5), Engine #2 (5), Engine #3(2)) | 9,000 ea | Cash Reserve |  |  | 18000 | 18000 | 18000 | 10000 | 10000 | 10000 | 20000 | 10000 | 10000 | 10000 | 10000 | 10000 | 20000 | 10000 | 10000 | 10000 | 10000
Air Tanks |  |  | 15 | Need 51 Air Tanks (3 for each air pack) | 1,500 ea | Cash Reserve |  |  | 9000 | 9000 | 4500 | 4500 | 4500 | 4500 | 9000 | 4500 | 4500 | 4500 | 4500 | 4500 | 9000 | 4500 | 4500 | 4500 | 4500
Turnout Gear |  |  | 10 | Need 25 sets, one set required for each fire fighter, | 4000 | Cash Reserve |  |  | 12000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
Infrastructure
Replace shingles on addition | [8 empty] | FY24: 5000
Replace shingles on main structure | [8 empty] | FY27: 45000
New addition to accommodate longer trucks | [8 empty] | FY29: 400000
Trade-in
Unnasinged Funds | [8 empty] | FY23: -54879
Capital Reserves used (Equipment) | [8 empty] | 0 | -25000 | -267230 | 0 | -745000 | 0 | 0 | 0 | -520000 | 0 | 0 | 0 | -1200000 | -25000 | 0 | -900000 | 0
Capital Reserves used (Infrastructure) | [8 empty] | 0 | -5000 | 0 | 0 | -45000 | 0 | -400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety Equipment Reserves used | [8 empty] | -39000 | -35000 | -30500 | -22500 | -22500 | -22500 | -37000 | -22500 | -22500 | -22500 | -22500 | -22500 | -37000 | -22500 | -22500 | -22500 | -22500
Remaining balance | [8 empty] | 72075 | 62198 | 60763 | 59542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan Payments from Taxes | [8 empty] | FY23: -63675; FY24: -62198; FY25: -60763; FY26: -59542
Payment from Taxes | [8 empty] | FY23: -8400
Reconciliation | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital Reserves raised from taxes | [8 empty] | -55000 | -150000 | -250000 | -250000 | -250000 | -250000 | -250000 | -275000 | -275000 | -275000 | -275000 | -275000 | -300000 | -300000 | -300000 | -300000 | -300000
Safety Equipment Reserves raised from taxes | [8 empty] | -40000 | -40000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000 | -35000
Total Taxes raised | [8 empty] | -167075 | -252198 | -345763 | -344542 | -285000 | -285000 | -285000 | -310000 | -310000 | -310000 | -310000 | -310000 | -335000 | -335000 | -335000 | -335000 | -335000
Capital Reserves at FY end | [7 empty] | 153233.33 | 208233.33 | 328233.33 | 311003.33 | 561003.33 | 21003.33 | 271003.33 | 121003.33 | 396003.33 | 151003.33 | 426003.33 | 701003.33 | 976003.33 | 76003.33 | 351003.33 | 651003.33 | 51003.33 | 351003.33
Safety Equip Reserves at FY end | [7 empty] | 2080 | 3080 | 8080 | 12580 | 25080 | 37580 | 50080 | 48080 | 60580 | 73080 | 85580 | 98080 | 110580 | 108580 | 121080 | 133580 | 146080 | 158580
Total Reserves | [7 empty] | 2080 | 3080 | 8080 | 12580 | 25080 | 37580 | 50080 | 48080 | 60580 | 73080 | 85580 | 98080 | 110580 | 108580 | 121080 | 133580 | 146080 | 158580
Note on N9: Finance: Change from 500,000 to 600,000 plus 100,000 down deposit in FY24.
Note on J11: Finance: No deposit required Ordered but Truck not available until FY25
Note on K11: Finance: Truck not available until FY25
Note on L11: Finance: Originally thought it would be 200K. The bid came in at 267,230.
Note on J21: Finance: Unable to obtain in FY22, board approved to purchase in FY23 with unassigned funds
Note on J23: Finance: Through budget equipment line
Note on A37: Finance: Put sale of property back into the capital reserve as that is where the expense comes from in the future.
Note on K39: Finance: Jaws of Life 25K Rescue Truck Deposit 100K
Note on L39: Finance: Down Deposit on Rescue Truck for FY27

## FY24 Town Center
TOWN CENTER FUND | Year of Equipment | FY Acquired | Estimated Life | Description | Acquired Amount | Payment Source Status | Beginning Reserve Balance | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39
Utility Expenses | [7 empty] | 23000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000
Insurance | [7 empty] | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100 | 6100
Building Maintenance | [7 empty] | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
Loan | [9 empty] | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000
Planned Library & Town Center Renovations | [7 empty] | FY23: 257600
Town Center Funds used | [7 empty] | -301700 | -43100 | -163100 | -163100 | -163100 | -163100 | -163100 | -103100 | -103100 | -103100 | -103100 | -103100 | -103100 | -103100 | -103100 | -103100 | -103100
Remaining balance | [7 empty] | 0 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000
Payment from Taxes | [7 empty] | 0 | 0 | -150000 | -150000 | -150000 | -150000 | -150000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000
Reconciliation | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Taxes raised | [7 empty] | 0 | 0 | -150000 | -150000 | -150000 | -150000 | -150000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000
Town Center Rents coming in | [7 empty] | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073 | -109073
Fund Balance at FY end | [6 empty] | 430781 | 238154 | 304127 | 250100 | 196073 | 142046 | 88019 | 33992 | 39965 | 45938 | 51911 | 57884 | 63857 | 69830 | 75803 | 81776 | 87749 | 93722

## FY24 Administration
ADMINISTRATION EQUIPMENT | Year of Equipment | FY Acquired | Estimated Life | Description | Acquired Amount | Curent Payment Source | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39 | FY40
Copier #1 | 2021 | FY21 | 6 | Clerks Office | 3744 | Cash GF | FY28: 7500; FY34: 10000; FY40: 10000
Copier #2 | 2013 | FY13 | 6 | Small Conference Room | 3449 | Cash GF | FY24: 5000; FY30: 10000; FY36: 10000
Copier #3 |  |  | 6 | Planning & Zoning office | 4302 | Cash GF | FY23: 7500; FY32: 10000; FY38: 10000
Server | 2016 | FY16 | 6 | Serves Finance, Clerk, Town Manager, Assistant to Town Manager, Planning & Zoning | 7500 | Cash GF | FY23: 10000; FY29: 15000; FY35: 20000
Computers desk tops |  |  | 4 | Need 9(1,500/ea) |  | Cash GF | 1500 | 3000 | 4500 | 4500 | 2000 | 4000 | 6000 | 6000 | 2500 | 5000 | 5000 | 7500 | 3000 | 6000 | 9000 | 6000 | 9000 | 6000
Computers lap tops |  |  | 4 | Need 4 (1,500/ea) |  | Cash GF | FY24: 1500; FY26: 4500; FY28: 1700; FY30: 5100; FY32: 1900; FY34: 5700; FY36: 2100; FY38: 2100; FY40: 2100
Phone System |  |  | 15 |  |  | Cash GF | FY23: 10000
Unnasinged Funds | [6 empty] | FY23: -20000
Remaining balance | [6 empty] | 9000 | 9500 | 4500 | 9000 | 2000 | 13200 | 21000 | 21100 | 2500 | 16900 | 5000 | 23200 | 23000 | 18100 | 9000 | 18100 | 9000 | 18100
Payment from Taxes | [6 empty] | -1500 | -9000 | -4500 | -13500 | -2000 | -10300 | -6000 | -26700 | -2500 | -11500 | -5000 | -17900 | -3000 | -12800 | -21000 | -12800 | -21000 | -12800
Reconciliation | [6 empty] | 7500 | 500 | 0 | -4500 | 0 | 2900 | 15000 | -5600 | 0 | 5400 | 0 | 5300 | 20000 | 5300 | -12000 | 5300 | -12000 | 5300
Total Taxes raised | [6 empty] | -1500 | -9000 | -4500 | -13500 | -2000 | -10300 | -6000 | -26700 | -2500 | -11500 | -5000 | -17900 | -3000 | -12800 | -21000 | -12800 | -21000 | -12800
Note on H7: Finance: Move from FY26 Waiting for estimates
Note on K7: Finance: Move to FY23 - waiting for estimate $7,500
Note on E12: Finance: Listers (1) Finance (1) Clerk (1) Asstant Clerk (1) Public (1) Town Manager (1) Admin Assisant (1) Town Planner (1) Zoning Administrator (1)
Note on E14: Finance: Town Manager Town Clerk Town Planner/Zoning Administrator

## FY24 General Summery
CAPITAL TAX CONTRIBUTIONS |  | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39
| Highway Capital Equipment | -132945 | -227433 | -200000 | -225000 | -225000 | -225000 | -200000 | -200000 | -200000 | -200000 | -200000 | -225000 | -225000 | -225000 | -225000 | -225000
| Highway Infrastructure | -677073.91 | -719284.27 | -722558.99 | -725749.27 | -611896.25 | -609842.55 | -660090.26 | -658137.27 | -565272.26 | -515000 | -520000 | -535000 | -540000 | -540000 | -540000 | -540000
| Planning New Sidewalk Projects | -25000 | -25000 | -25000 | -25000 | -25000 | -25000 | -75000 | -75000 | -75000 | -75000 | -75000 | -100000 | -336400 | 0 | 0 | 0
| Police Capital | 0 | -100000 | -100000 | -112500 | -150000 | -150000 | -150000 | -165000 | -170000 | -170000 | -170000 | -187500 | -170000 | -170000 | -225000 | -245000
| Fire Capital | -252198 | -345763 | -344542 | -285000 | -285000 | -285000 | -310000 | -310000 | -310000 | -310000 | -310000 | -335000 | -335000 | -335000 | -335000 | -335000
| Town Center & Library (loan) | 0 | -150000 | -150000 | -150000 | -150000 | -150000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000 | -210000
| TOTAL TAXES REQUIRED | -1087216.91 | -1567480.27 | -1542100.99 | -1523249.27 | -1446896.25 | -1444842.55 | -1605090.26 | -1618137.27 | -1530272.26 | -1480000 | -1485000 | -1592500 | -1816400 | -1480000 | -1535000 | -1555000
RESERVES BALANCES |  | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39
| Highway Capital Reserve at FY end | 15701.04 | 163701.04 | 110951.04 | 170951.04 | 385951.04 | 20951.04 | 18951.04 | 133951.04 | 333951.04 | 76951.04 | 74201.04 | 189201.04 | 104201.04 | 114201.04 | 54201.04 | 279201.04
| Highway Bridge & Culvert Reserves at FY end | 418926 | 493926 | 568926 | 643926 | 718926 | 793926 | 918926 | 43926 | 43926 | 43926 | 43926 | 43926 | 43926 | 43926 | 43926 | 43926
| Highway Guardrail Reserves at FY end | 29016 | 16 | 10016 | 20016 | 16 | 10016 | 20016 | 30016 | 40016 | 50016 | 60016 | 80016 | 100016 | 120016 | 140016 | 160016
| Planning New Sidewalk Reserves at FY end | 48750 | 57500 | 49650 | 41800 | 50200 | 58600 | 133600 | 208600 | 283600 | 358600 | 433600 | 533600 | -130000 | -130000 | -130000 | -130000
| Police Capital Reserve at FY end | 87533 | 70183 | 11883 | 28583 | 3483 | 61683 | 17383 | 64883 | 18883 | 75383 | 7083 | 51083 | 41183 | 71083 | 2683 | 72983
| Fire Capital Reserves at FY end | 328233.33 | 311003.33 | 561003.33 | 21003.33 | 271003.33 | 121003.33 | 396003.33 | 151003.33 | 426003.33 | 701003.33 | 976003.33 | 76003.33 | 351003.33 | 651003.33 | 51003.33 | 351003.33
| Fire Safety Equip Reserves at FY end | 8080 | 12580 | 25080 | 37580 | 50080 | 48080 | 60580 | 73080 | 85580 | 98080 | 110580 | 108580 | 121080 | 133580 | 146080 | 158580
| Town Center Fund | 304127 | 250100 | 196073 | 142046 | 88019 | 33992 | 39965 | 45938 | 51911 | 57884 | 63857 | 69830 | 75803 | 81776 | 87749 | 93722
| TOTAL RESERVES AT YEAR END | 1240366.37 | 1359009.37 | 1533582.37 | 1105905.37 | 1567678.37 | 1148251.37 | 1605424.37 | 751397.37 | 1283870.37 | 1461843.37 | 1769266.37 | 1152239.37 | 707212.37 | 1085585.37 | 395658.37 | 1029431.37

## 15 year interest
Interest or Administrative Fees spent since 2006
EQUIPMENT |  | Status A=Active C=complete | Last Installment | Paid as of FY21
Highway
| Equipment Note | C |  | 29922.18
| Excavator (2013) | C |  | 8033.49
| Grader (2017) | A | FY24 | 10012.61
| Loader (2014) | C |  | 1086.57
| Dump Truck (2011) | C |  | 1754.55
| Dump Truck (2012) | C |  | 2984.26
| Dump Truck (2019) | A | FY24 | 8654.15
| Dump Truck (2020) | A | FY25 | 3876.71
| Chevy PU (2017) | C |  | 181.56
| Tractor | C |  | 336.9 | 66842.98
Fire
| 2005 Engine | A | FY26 | 77100.16
| 2011 Engine | C |  | 5015.45
| 2015 Engine | C |  | 13654.48
| 2018 Engine | A | FY26 | 25047.53 | 120817.62
Police
| Camcorders | C |  | 1450.6
| Cruiser Lease | C |  | 5410.97 | 6861.57
| TOTAL EQUIPMENT INTEREST |  |  |  |  | 194522.17
BUILDINGS & INFRASTRUCTURE
| Highway |  |  | 80822.93
| Depot | C |  | 7023.27
| Millett Street AR1-058 | A | FY32
| Jericho Rd | A | FY32 | 181820.39 | 269666.59
Library
| Building | C |  | 17711.08 | 17711.08
| TOTAL BUILDING & INFRASTRUCTURE INTEREST |  |  |  |  | 287377.67
| GENERAL FUND TOTAL |  |  |  |  | 481899.84
BUILDINGS & INFRASTRUCTURE
Water & Sewer
| Water Tank GAP | A | FY25
| Phosphorus RF1-074 | A | FY26
| East Main St. Planning RF1-101 | A | FY27
| Millett Street AR1-058 | A | FY32
| Jericho Road | A | FY32
| East Main St. RF3-335 | A | FY47
| Water Tank RF3-302 (0% interest) | A | FY48
| Bridge Street RF3-365 (0% interest) | A | FY60
| Bridge Street RF3-444 | A | FY61
| Revolving Loan/Bond Bank |  |  | 243545.88 | 243545.88
| WATER & SEWER TOTAL |  |  |  |  | 243545.88
| TOTAL GENEARL & WATER & SEWER |  |  |  |  | 725445.72