## Sheet1
| Richmond Transportation Committee Project Pipeline | [5 empty] | Updated: 8/25/2022
Project Name | Project Description | Capital Budget Item | Project Initiation | Phase * | Phase Completed | Report | Next Steps | Estimated Cost | Grant Funding
Bridge Street - East Side New Sidewalk | New sidewalk on east side of Bridge Street between Jolina court and Esplanade Street |  | 2021 | SC | 2022-06-01 | TO BE ADDED | 8/22-Did not get Vtrans construction funding; seek other funding | 400000 | TBD
Bridge Street Redesign - Complete Streets | Identify and prioritize multi-modal improvements to Bridge Street corridor |  | 2020 |  | 2021-06-01 | https://studiesandreports.ccrpcvt.org/wp-content/uploads/2021/09/20210827_RichmondBridgeStreet_ScopingMemo_WithAppendices.pdf |  |  | FY21 UPWP
A. East side of Bridge Street | From Route 2 to Jolina Court |  |  | SC |  |  | Seek funding for new 5’ sidewalk and 5’ uphill bike lane | 290866
B. Jolina Ct & Railroad Street | intersection of Jolina Court and Railroad Street |  |  | SC |  |  | Add pedestrian crossings (to Jolina Ct) and improve crossings (Railroad Street) | TBD
C. intersection of Cochran Road and Huntington Road | Intersection includes Bridge Street, Thompson Road, Huntington Road, and Cochran Road |  |  | SC |  |  | Pursue No Build alternative with enhancements for pedestrian and bike safety | TBD
Jericho Road New Construction | Construct new sidewalk on Jericho Road from the school entrance to Valley View Road | FY27 | 2021 | SC | 2022-06-22 | TO BE ADDED | Get funding for box rail sidewalk, with five-foot path and green strip where feasible | $520,000 Const./ $720,000 Total | FY22 UPWP
Huntington Road to Johnnie Brook trail | Huntington Road from Farr Complex to the Cross Vermont Trails trailhad at Johnnie Brook trail | FY27 | 2021 | SC | 2022-06-22 | TO BE ADDED | Additional scoping study needed for "S" curve area; Funding to be sought |  | FY22 UPWP
East Main Street south side | Re-construct sidewalks on south side of East Main Street btween Bridge Street & Harrington's |  | 2021 | IC | Scheduled for construction | https://www.richmondvt.gov/fileadmin/files/Archive/2018/11/3f-Richmond-Highway-restructuring-and-staffing-proposal.pdf | Town Highway Dept. to do project at the conclusion of the Route 2 repaving project | 283543 | No grant funding, covered in town budget
Bike/Ped Master Plans | Master Complete Streets plan to guide the for ped and bike on and off-road connections and trails
A. Northern Area | Master Plan covers area north of Winooski River |  | 2020 | PL | 2022-06-21 | https://www.ccrpcvt.org/wp-content/uploads/2021/07/Richmond_BikeWalkTrailsPlan_Phase1_20210617.pdf | Complete Southern Area project |  | FY21 UPWP
B. Southern Area | Master Plan covers area south of Winooski River |  | 2021 | PL | Expected 9/22 | TO BE ADDED | Sept 2022 - report to Selectboard and complete report |  | FY22 UPWP
Route 2 Targeted Scoping for Improving Shoulder Widths | Increase shoulder width at specific points between Village and Park and Ride, following the VTrans repaving project of Route 2 |  | 2022 | SC |  |  | Project begins fall 2022; Coordinated with CCRPC |  | FY23 UPWP
Bike/Ped Master Plans into Official Map | Official Map to regulate development of infrastructure and could cover ped and bike enhancements |  | 2022 | PL |  |  | Project begins January 2023 with CCRPC staff; will coordinate with Planning Commission |  | FY23 UPWP
Richmond Gateway Scoping Study | Bicycle and pedestrian connections between Richmond Village, elementary/middle school campus, mobile home park and the exit 11 Park and Ride. Uses 2014 study and 2021 Bike/Ped Master Plan North End reports |  | 2022 | SC |  |  | Projects begins fall 2022 |  | FY23 UPWP
Town Plan Goals & Objectives Review | Town Plan: review goals and objectives related to transportation planning |  | 2021 | PL | 2021-08-10 | Document submitted to Planning Commission | Annual Review and/or Planning Commission request
CCRPC Regional Park & Ride Richmond Priorities | RTC Review Richmond specific park & ride elements in current plan |  | 2022 | PL | 2022-07-12 | SEE CCRPC WEB SITE | Additional review per CCRPC requests
Richmond Capital Budget/Plan | RTC review and recommend items |  | 2021 | PL | 3/1/2021 Reviewed FY23 Plan | SEE TOWN WEB SITE FOR CURRENT PLAN | RTC review FY24 Plan in Sept 2022
Green Mountain Transit Richmond Services | Green Mountain Transit Plan with Richmond element |  | 2022 | PL | Part of FY23 UPWP GMT Grant |  | Work with
Walkability Audit Project and Report | Audit to assess quality needed improvements for ped and bicycle infrastructure |  | 2022 | PL | audit completed summer 2022 | Expected Fall 22 | Complete report for RTC review
Committee Documents
A. Purpose Statement | Created short and long versions |  |  | PL | 2022-03-08 |  | Update as needed | NA
B. Transportation Implementation Plan | Created and provided to Selectboard |  |  | PL | 2020-06-04 | Provided to Selectboard | Update as needed | NA
* Phases: PL = Planning; Project Design/Definition=PD; Scoping=SC: Engineering=EN; Permitting=PT; In Construction=IC; Maintenance& Operation=MO